## Result FR
Results Framework for your Mazingira CBO waste management project, structured to align with best practices in M&E in community engagement:
Results Framework for Mazingira CBO Waste Management Project
Goal: To promote sustainable waste management practices in Mtongwe and Likoni through improved sorting, recycling, and civic engagement.
1. Project Logic
Inputs | Activities | Output | Outcome | Impacts
Project staff (you) | Community training workshops | - 500+ households trained | - 30% reduction in sorting errors | 40% increase in recycling rates
Kobo Toolbox | - Door-to-door waste audits | - Monthly audit reports | - 20% more HHs adopt recycling | Reduced illegal dumping
Excel/Power BI | - Civic education campaigns | - 10 FGDs conducted | - Increased awareness (survey) | Policy changes (e.g., local ordinances)
2. Outcome Indicators (What to Measure)
Outcome | Indicator | Target | Data Source | Responsible Party
Improved waste sorting | % decrease in observed sorting errors | 30% | Kobo field audits | Paul + Field Team
Increased recycling | # households separating waste | 200 HHs | Sign-up forms (Excel) | Volunteers
Enhanced accountability | # community feedback sessions held | 10 sessions | FGD reports | Mazingira CBO
3. Data Flow & Analysis
Step 1: Collect data via Kobo
Step 2: Clean/analyze in Excel
Step 3: Visualize trends in Power BI (e.g., charts of recycling participation).
Step 4: Share findings at monthly community meetings
4. Assumptions & Risks
Risks | Mitigation Strategy
Low participation | Partner with youth groups
Data inconsistencies | Train volunteers on Kobo
5. Learning & Adaptation
Monthly: Review Excel dashboards to adjust training focus.
Quarterly: Host "Data Days" with community to co-interpret results.

## Logical FR
Logical Framework (Logframe) for Mazingira CBO waste management project, structured to align with international M&E in community work:
Logical Framework for Mazingira CBO Waste Management Project
Project Goal: Improve environmental and public health through sustainable waste management in Community Name
Hierachy | Objectively Verifiable Indicators (OVIs) | Means of Verification (MoV) | Assumptions/Risks
GOAL
Environmental: 40% less illegal dumping Health: Reduced waste-borne diseases Economic: 20 new green jobs | - 40% reduction in illegal dumping by 2025 | - County govt. reports | Political will supports waste reforms
| - Local policy changes adopted | Clinical health reports
OUTCOMES
Behavioral: 30% fewer sorting errors Social: 200+ HHs adopt recycling Political: 2 policy recommendations submitted | 1. 30% fewer sorting errors in 500+ HHs | - Kobo audit reports | Community sustains practices post-project
| 2. 200+ HHs adopt recycling | - Excel HH registers
| 3. 10+ youth trained as waste champions | - Training certificates
OUTPUTS
500+ households trained (tracked in Excel, like Mazinqira Safi) 1 waste sorting facility established (partner with county govt.) 4 quarterly progress reports | 1. 12 training sessions conducted | - Attendance sheets | Partners provide timely resources
| 2. 50 waste bins distributed | - Asset register
ACTIVITIES
Monthly waste audits: Digital data collection via Kobo (your expertise) Community trainings: 12 workshops Youth mobilization: Recruit/mentor 10 waste champions Advocacy meetings: Present data to local govt. | 1. Door-to-door waste audits (monthly) | - Field schedules | Field staff retention >80%
| 2. Civic education workshops | - Workshop reports
| 3. Youth volunteer recruitment | - Volunteer database
INPUTS
Human: You (M&E lead), 10 volunteers and 20 members.Tools: Kobo Toolbox ( Excel/Power BI. Materials: 150 waste bins, training manuals